## Sheet1
Sl. No. | Month | Task Name | SubTask | Allocated Date | Target Date of Completion | Allocated To | Status (Completed /Pending) | Reason for Pending
1 | January | Project Briefing | Live Meeting | 2024-01-24 | 2024-01-31 | Entire Team | Completed | -
2 |  | Project Initiation | Live Meeting | 2024-01-31 | 2024-02-01 | Entire Team | Completed | -
3 | February | Data Collection | Surf the Internet for collecting Datasets |  |  | Subham, Harshit | Completed | -
4 |  | Data Preprocessing | Implemented Dataset in Python | 2024-02-07 | 2024-02-08 | Harshit | Completed | -
5 |  | Guidance Connect | Zoom Call | 2024-02-11 | February 11, 2024 | Lokesh, Harshit, Subham, Khushi | Completed | -
6 |  | Preparing Synopsis | Implement the project as an outline. | 2024-02-14 | 2024-02-15 | Entire Team | Completed | -
7 |  | Project EDA Preparation | Expressing the train and test data as visualizations | 2024-02-16 | 2024-02-20 | Lokesh, Harshit | Completed | -
8 |  | Internal Exams! | - | 2024-02-21 | 2024-02-24 | Entire Team | Completed | -
9 | March | Model Building | Prepared our model for the predictive maintenance. | March 1, 2024 | 2024-03-10 | Lokesh | Completed | -
10 |  | Doubt Clarification Call | Discussed queries regarding model implementation. | 2024-03-11 | 2024-03-11 | Entire Team | Completed | -
11 |  | Preparing LLD | Implemented the models and EDA as project documentation in low level design. | 2024-03-12 | 2024-03-27 | Harshit | Completed | -
12 |  | LLD Submission | ~ | March 28, 2024 |  | Entire Team | Completed | -
13 |  | HLD Preparation | Implemented the models and accuracy analysis as project documentation in the High Level design. | March 24 2024 |  | Harshit, Lokesh | Completed
14 |  | HLD Submission | ~ | April 9th 2024 | April 9th 2024 | Harshit, Lokesh | Completed | -
15 |  | MidReview Call | ~ | March 30, 2024 |  | Lokesh, Harshit, Subham, Dhruti | Completed | -
16 | April | Model Evaluation | Test the model and evaluate its accuracy | March 31st 2024 | April 1st 2024 | Lokesh | Completed
17 |  | GUI Preparation | A GUI to be made of 21 sensors as input data | April 1st 2024 | April 7th 2024 | Lokesh, Harshit | Completed
|  | Final Project Report Preparation | ~ | April 8th 2024 | April 9th 2024 | Harshit | Completed
18 |  | Internal Exams + Practicals | ~ | 2024-04-02 | 2024-04-10 | Entire Team | Completed | -