## Sheet1
Project name | Predictive Maintenance for Aircraft Engines & Aviation Safety
Supervisor/Guide Name(Department) | Dr. Pradipta Kumar Mishra
Mentor name(IBM) | Mr. Rithik Raj Vaishya
Team members | Lokesh Patra, Indigibilli Harshit, Subham Nayak, Khushi Singhania, Dhruti Deepam Mohaptra
Description | Aircraft maintenance is crucial for ensuring safety and reliability. To develop a data science model that predicts the likelihood of engine failure in aircraft based on sensor data, flight patterns, and historical maintenance records. The system should enable proactive maintenance scheduling, reducing unplanned downtime and improving overall aviation safety.
Slno | Task | Assigned to | Start date | End date | Status | Remarks
Week 1
DS Group 2 | Understand the project given to us and discuss within team mates on how to step wise progress with it. Basically we need to make a project flow document or synopsis on the topic. | All team mates | January 24th 2024 | February 07th 2024 | Assigned
Week 2
DS Group 2 | Data set collection from various sources like repositories, and papers. | Subham & Harshit | February 07th 2024 | February 11th 2024 | COMPLETED
Week 3
DS Group 2 | We've completed the foundational steps of a typical machine learning workflow, including identifying labels and targets, training and testing our model. Simultaneously, we've crafted and finalized our project synopsis, ensuring its completion within our set timeframe, and submitted it through the designated portal. | Lokesh, Subham, Harshit, Khushi | February 13th 2024 | February 20th 2024 | COMPLETED
Week 4
DS Group 2 | Prepared our model for the predictive maintenance. Implemented the models and EDA as project documentation in low level design.Implemented the models and accuracy analysis as project documentation in the High Level design. | Harshit, Lokesh | February 24th 2024 | March 10th 2024 | COMPLETED
Week 5
DS Group 2 | We are actively developing the low-level design of our project, having meticulously crafted process flow diagrams and completed the associated documentation well within the allocated deadline. | Harshit, Lokesh | March 12th 2024 | March 28th 2024 | COMPLETED
Week 6
DS Group 2 | We are actively developing the high-level design of our project, having meticulously crafted process flow diagrams and completed the associated documentation well within the allocated deadline. We are currently engaged in crafting the final project report of our project , with an anticipated completion date set for April 10, 2024. | Harshit, Lokesh | March 30th 2024 | April 10th 2024 | COMPLETED